## Sheet1
Common Good Consutlation
Greenside Park, Newmilns
2023-03-06
7pm-8.30pm
Speaker (Organisation) | Point | Brief
Craig Fulton (EAC) | Introduction
Lisa Fulton (CATARA) | Introduction
Yvonne (Community Council) | Point of note | Community Council were unaware of the proposal and the point of the meeting.
Craig Fulton (EAC) | Point of note | Indicated that a consultation had been requested to be sent to the Community Council and apologised if that had not been received. Consultation would be sent to CC as a matter of course
| Action | Confirmation that CC had been sent a consultation on 31 January. Further consultation was sent to the CC following meeting.
Ian Storrar (Resident) | Objection | The play park screens will be directly outside someones window with flashing lights.
Lisa Fulton (CATARA) | Response | It is a panel which we will show you a video of so you can see what it looks like.
| Action | Video link here
Unkown (resident) | Objection | How are people to know about the project. Signage was torn down in the park, only residents at persian sands received consultation documents.
Craig Fulton (EAC) | Response | As indicated the consutlation was on the site itself, there is a consultation online which people can access, the consultation was orginally in all shops including premier stores, in the window of the undertaker and is being promoted online. However given the feedback we will look to put back up on site, reciruclate round the shops and localities and engage with local partners to increase the circulation through social media. EAC would be keen to hear if there are specific places which residents felt would enable the locality to engage and an offer was made to leave suggestions.
| Action | All site notices re-applied, TARA circulated the information again to partners and through the local shops.
Ian Storrar (Resident) | Objection | Where is this play park going if it is not going to be in front of residents windows? Is there flashing lights on it? People will look at this out fo their window.
Lisa Fulton (CATARA) | Response | There isnt as such flashing lights, the panels light up but they don’t flash. The play park can be controlled in order that it is only on during reasonable times. It can be programmed to come off before 9pm or before it is dark in the winter.
Craig Fulton (EAC) | REsponse | Ian is there some reasonable compromise which you, as a resident, would be willing to make in terms of the time of operation?
Ian Storrar (Resident) | Response | I don’t want to be seeing these flashing lights when I am sitting watching television.
Ian Storrar (Resident) | Objection | [discussed a recent incident in the area] You would be bringing more ASB to the area.
Unkown (resident) | Response | That has nothing to do with a weans play park so you cant compare those two things.
Craig Fulton (EAC) | Response | As it relates to the initial objection the CATARA can consider this and potenially make additions to their plans to consider some screening of the site. In terms of ASB this isnt something which can be asnwered by the CATARA instead we will relay these objections to the Police and they will respond.
Unkown (resident) | Question/ Objection | What will the noise level be? Looked at technical specs and the video on the website however the music drowned out the noise that the equipment made. Concerned about the noise level of the football panel for people close to the park, people on night shift. Noise would also reverberate through the viaduct.
Craig Fulton (EAC) | Response | We can get a different video circulated and can get input from Environmental health in terms of the noise in order that we can get a comparitive consdieration to allow better understanding.
Unkown (resident) | Objection | Objection was regarding the construction of the playpark
Craig Fulton (EAC) | Response | The building elements would be covered by any contractor to ensure that it was safe. Emphasise on community consultation and this would be further down the road.
Unkown (resident) | Objection | Young people hanging around the arches at the weekend drinking, setting fires etc additional play park equipment would attract more issues.
Lisa Fulton (CATARA) | Response | Timings could be set on the park to ensure it is turned off at times when young people are engaging in Anti Social Behaviour.
Unkown (resident) | Objection | Can it be switched off in the afternoon if young people are congregating and causing issues?
Unkown (resident) | Response | They are already doing this before the equipment is in so what change would it make?
Unkown (resident) | Response | We don’t have a back garden so are we just to sit and listen to it?
Craig Fulton (EAC) | Response | People are indicating that the site suffers from ASB and are concerned that the play equipment could make that worse. That is perfectly reasonable question however it is not one for the TARA more one which we can pose to Police colleagues and Community Safety team.
Unkown (resident) | Objection | What about the toilet facilities?
Craig Fulton (EAC) | Response | Again, there is a reasonable complaint that there is ASB in the park in you are indicating that facikities don’t exist on the site. Installing toilets for the site would not be something that the TARA would consider given this is an addition to an exisisting play park. This will be relayed
Lisa Fulton (CATARA) | Response | CATARA were formed to help solve ASB in our community so we understand the issues taking place and have worked hard to combat these in our community.
Unkown (resident) | Objection | The site you are proposing had a no balls game sign.
Craig Fulton (EAC) | Response | We will engage with Greener Communities in terms of the signage and the reasons that this has not been replaced.
Ian Storrar (Resident) | Question | Once the transfer is complete who is responsible for the litter?
Lisa Fulton (CATARA) | Response | Greener Communities remain responsible for the collection of litter.
Unkown (resident) | questions | There isnt enough bins onsite.
Craig Fulton (EAC) | Response | So there are questions in relation to the responsibility for picking up the litter and this has been confired as still being the responsibility of the Council and in terms of the number of bins it has been indicated that some residents don’t feel there is enough so I will check this with colleagues in Greener Communities.
Unkown (resident) | Question | So if the community asset transfer is approved does this mean that the group are responsible for the upkeep of the play park?
Lisa Fulton (CATARA) | Response | Yes we would be responsible for the play park however the council would remain responsible for the grass cutting and the litter picking/bins.
Unkown (resident) | Question | So if something goes wrong with the park that would be for your group to make repairs?
Lisa Fulton (CATARA) | Response | Yes we would initially have a 5 year warranty which we would extend in due course.
Unkown (resident) | Question | So what happens over the time when the CATARA don’t have the ability to make the repairs due to personel leaving or the organisation folding?
Craig Fulton (EAC) | Response | Any community asset transfer application has a clause which indicates that the group have to return the land to the original condition. There is potetnial that, if the CATARA decide to give up the lease then there is potetnial that, given the equipment is from our contractor that if Greener Communities were happy with the condition they could choose to include it under our maintenance contract. It should be noted that this isnt an agreement that we would more just an indication that the opportunity may exist.
Mr Barber | Question | Concerns about young people around the park causing damage to proporty and the potetnial for the park to be wrecked quickly.
Craig Fulton (EAC) | Response | Thank you for this contribution as previously indicated any objection based on ASB for the site would be referred to Police Scotland to comment on.
Unkown (resident) | Question | Does it concern you that it is so close to the kids park? The age group of 10-16 will be mixing with young kids at 2-3 yrs. This could lead to bad language in the park or someone getting a ball in the face.
Craig Fulton (EAC) | Response | We can look to provide some examples or evidence where these equipment can coexist safely and add value to parks.
Lisa Fulton (CATARA) | Response | These cases would only be with the Football panel. If it would be preferable we could just put the memo equipment in so that this couldn’t happen.
Unkown (resident) | Question | Is there other equipment which could go in instead of the Suto (Football Panels)?
Unkown (resident) | Response | There is an issue with a football panel near a river as …..might kick it in the river and fetch.
Conversation about when the consultation has taken place in terms of the development of the project which doesn’t form part of the objection
Unkown (resident) | Question | I think another issue is parking
Craig Fulton (EAC) | Response | We will engage with ARIA and consider this objection.
Craig Fulton (EAC) | Response | I appreciate we have been through the mill here with the consultation however I think we have reached the stage that it is a relatvely reasonable discussion. While I think both EAC and the TARA can see there are some concerns I believe there is already proposals and changes which have been indicated as part of the consultation which the CATARA can take back and make amendments to their proposal or add addtioinality to deal with audio or visual issues which residents percieve to be a problem and come back to you with amendments. Given the discussions which will be ongoing and picking up on some concerns that individuals have not had access to the materials including the community council. Once that has been rectified and a new proposal circulated we will encourage feedback from residents on the plans to consider whither your objections remain or alternatively if your concens have been satisfied. I would like to thank you for your time, invite you to leave an email contact if you havent already engaged to help with ciruclation of information otherwise bring the meeting to a close.
Meeting finished.